## Tabelle1
No. | Risk | Prob. occurrence | Damage (0-10) | Risk factor | Risk minimation | Person in change
1 | Team members lack of specialized skill required by the project | 95% | 6 | 5.7 | Plan in time at each task for research. If possible assign a member with prior knowledge. | Alex
2 | Personnel shortfalls | 90% | 2 | 1.8 | Plan in shortfalls and plan without too many dependencies. | Alex,Jennifer
3 | Inexperience project managers | 75% | 2 | 1.5 | Clarify goals with each teammember. Talk about upcoming problems / risks in the complete team. | Jennifer
2 | System requirement not adequately identified | 25% | 4 | 1 | Research and adjust requirements while developing. | Alex
5 | Server crash | 10% | 5 | 0.5 | Use a server hoster with failsave mechanisms. Have direct contact to the server hoster for quick fixes. | Jenny
6 | limited time on project | 30% | 3 | 0.9 | Always plan in time buffers. Use experience from previous use-cases for time guessing. | Jennifer
7 | Bad code quality | 30% | 3 | 0.9 | Use clean code standards. Refactor code. | Alex
8 | Unoptimal team constallation | 75% | 1 | 0.75 | Define tasks for each team | Alex
9 | Loss of Code-Data | 2% | 10 | 0.2 | Code repository is on GitHub and each member has a local copy. Creating backups to minimize loss. | Alex,Jennifer
10 | Fail of dev-tools | 10% | 1 | 0.1 | Only use widespread tools that already prooven stable. | Alex