## Tabelle1
No. | Risk | Prob. occurrence | Damage | Risk factor | #Risks | Pareto
1 | Team members lack of specialized skill required by the project | 95% | 40 | 38 | 10 | 20%
2 | Personnel shortfalls | 100% | 8 | 8 |  | 2
3 | Inexperience project managers | 75% | 7 | 5.25
2 | System requirement not adequately identified | 25% | 20 | 5
5 | Missing communication between team members | 20% | 17 | 3.4
6 | limited time on project | 30% | 10 | 3
7 | Project progress not monitored closely enough | 75% | 3 | 2.25
8 | unoptimal team constallation | 25% | 4 | 1
9 | interface requirements and implementation unknown | 90% | 1 | 0.9
10 | Missing communication between teams | 75% | 1 | 0.75